## Task-sheet
Tasks Table
Key Stakeholders |  | Raj, Sam, Mahn, Kim, Zuhun, Mark, Ruther
ID | Task Name | Owner | Start Date | End Date | Actual | Estimate | Status
1 | Analysis | Neel | 2020-10-02 | 2020-10-29 | 35 | 45 | l
2 | Testing | Kate | 2020-10-10 | 2020-10-26 | 20 | 25 | l
3 | Analysis | Kate | 2020-10-12 | 2020-10-15 | 78 | 75 | l
4 | Team reporting | Siya | 2020-10-11 | 2020-10-25 | 0 | 16 | l
5 | Generate documentation | Siya | 2020-10-15 | 2020-11-06 | 0 | 0 | l
6 | Code review | John | 2020-11-09 | 2020-11-11 | 0 | 0 | l
7 | Test analysis | John | 2020-11-22 | 2020-12-01 | 0 | 0 | l
8 | Generate test report | Neel | 2020-12-02 | 2020-12-07 | 0 | 0 | l
9 | Execute | Neel | 2020-12-10 | 2020-12-23 | 0 | 0 | l
10 | Requirement gathering | Ron | 2020-10-05 | 2020-10-23 | 0 | 53 | l
11 | Requirement analysis | Ron | 2020-10-06 | 2020-10-27 | 0 | 44 | l
12 | Project closure | Ron | 2020-12-25 | 2020-12-25 | 1 | 0 | l

## WSR-charts
Milestines and Key Dates |  |  |  |  | Resource Workload(Days)
1 | Development Complete | On Track | 2020-12-15 | Neel | 23
2 | Testing Complete | Pending | 2020-12-25 | Kate | 45
3 | Planning for design change | Concern | 2020-12-23 | Siya | 16
4 |  |  |  | John | 3
5 |  |  |  | Ron | 8
6
Task Meter
Tasks status - year 2020
On Track | 150
Pending | 54
Concerns | 20

## Action-sheet
Top 5 Concerns (Risk or issues)
ID | Task description | Task Type | Status
1 | The business requirements have not been signed off. | Initial Analysis | On Track
2 | The servers for the project have not been comisioned. | Support | Concern
3 | Business uers for testing are not allocated. | Initial Analysis | Delayed
4 | Check the impact on delivery dates on other dependant teams. | QA Lead | Concern
5
Open Actions and change requests
ID | Task description | Owner | Status
1 | Pending change request for new login screen. | Neel | On Track
2 | Tech architecture needs alignment need to be confirmed. | Architect | Concern
3 | Customer impact assesment. | Agile Team | Delayed
4 | Testing is not progressing as per the plan | Manager | Concern
5